## sample_schedule
activity_code | activity_name | wbs_id | duration_days | progress_percent | status | start_date | finish_date | responsible_party
ENG-001 | Existing Generator Survey | 10 | 5 | 100 | Completed | 2026-08-01 | 2026-08-05 | Engineering
ENG-002 | 3D Modeling | 11 | 10 | 60 | In Progress | 2026-08-06 | 2026-08-15 | CAD Team
ENG-003 | Reverse Engineering Drawings | 12 | 8 | 20 | In Progress | 2026-08-16 | 2026-08-24 | Engineering
MFG-001 | Machining | 13 | 12 | 0 | Not Started | 2026-08-25 | 2026-09-05 | Workshop
MFG-002 | Fabrication | 14 | 15 | 0 | Not Started | 2026-09-01 | 2026-09-15 | Fabrication Shop
ASM-001 | Mechanical Assembly | 15 | 7 | 0 | Not Started | 2026-09-16 | 2026-09-22 | Assembly Team
ASM-002 | Electrical Assembly | 16 | 6 | 0 | Not Started | 2026-09-20 | 2026-09-26 | Electrical Team
TST-001 | Factory Acceptance Test | 17 | 3 | 0 | Not Started | 2026-09-27 | 2026-09-30 | QA/QC